## Sprint 1
ITSC-3155 Software Engineering
Sprint Backlog (M-Sat)
Story Tasks | Story Point (Total, predicted) | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 | 16 | Andrew | 11 | 3 | 0 | 7 | 4 | 0 | 0 | Doing
Recommend new travel destinations based on previous travel |  |  | 6 | 3 | 0 | 2 | 1 | 0 | 0 | Done | Target: get done by Sprint 2 (work on now as well). 0 points left?
Recommended locations should be near previously-traveled locations |  |  | 5 | 0 | 0 | 2 | 3 | 0 | 0 | Doing | Target: get done by Sprint 2 (work on now as well). 5 points left?
User Story #2 | 12 | Landon | 8 | 3 | 1 | 2 | 0 | 2 | 0 | Doing
Display travel options at cheaper price points |  |  | 5 | 3 | 1 | 1 | 0 | 0 | 0 | Doing | Target: get done by Sprint 2 (work on now as well). 2 points left?
Display travel cheaper price combinations for travel (flight, hotel, destination) |  |  | 3 | 0 | 0 | 1 | 0 | 2 | 0 | Doing | Target: get done by Sprint 2 (work on now as well). 2 points left?
User Story #3 | 14 | Dhanush,Shashank | 14 | 6 | 3 | 3 | 0 | 2 | 0 | Doing
Allow users to select their desired hotel to stay at during their travel. |  |  | 9 | 6 | 3 | 0 | 0 | 0 | 0 | Doing | Target: get done by Sprint 1 - some rework needed, finish early in Sprint 2. 5 points left?
Allow users to select whether they would like to travel by plane or not. |  |  | 5 | 0 | 0 | 3 | 0 | 2 | 0 | Done | Target: get done by Sprint 1 - Done
User Story #4 | 12 | Ethan | 12 | 2 | 5 | 3 | 2 | 0 | 0 | Doing
Allow users to create and read reviews |  |  | 8 | 2 | 5 | 1 |  | 0 | 0 | Done | Target: get done by Sprint 1 - Done
Only allow users to write reviews on a travel destination if they have previously traveled there. |  |  | 4 | 0 | 0 | 2 | 2 | 0 | 0 | Done | Target: get done by Sprint 1 - Done
N/A
TOTAL |  |  | 45 | 14 | 9 | 15 | 6 | 4 | 0

## Sprint 2
ITSC-3155 Software Engineering
Sprint Backlog (M-Sat)
Story Tasks | Story Point | Assigned to | Estimated Effort (left) | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 | 16 | Andrew | 5 | 1 | 2 | 2 | 0 | 0 | 0 | Done
Recommend new travel destinations based on previous travel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done | Target: get done by Sprint 2 - Done
Recommended locations should be near previously-traveled locations |  |  | 5 | 1 | 2 | 2 | 0 | 0 | 0 | Done | Target: get done by Sprint 2 - Done
User Story #2 | 12 | Landon | 4 | 2 | 0 | 2 | 0 | 0 | 0 | Done
Display travel options at cheaper price points |  |  | 2 | 1 | 0 | 1 | 0 | 0 | 0 | Done | Target: get done by Sprint 2 - Done
Display travel cheaper price combinations for travel (flight, hotel, destination) |  |  | 2 | 1 | 0 | 1 | 0 | 0 | 0 | Done | Target: get done by Sprint 2 - Done
User Story #3 | 14 | Dhanush,Shashank | 5 | 3 | 0 | 2 | 0 | 0 | 0 | Done
Rework/refactor booking models |  |  | 5 | 3 | 0 | 2 | 0 | 0 | 0 | Done | Target: get done by Sprint 2 - Done
User Story #4 | 12 | Ethan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done
Allow users to create and read reviews | [9 empty] | Done | Done
Only allow users to write reviews on a travel destination if they have previously traveled there. | [9 empty] | Done | Done
Misc. Work |  |  | 24 | 5 | 0 | 4 | 3 | 5 | 7
DevOps, managing repository, creating presentation, etc. |  | All | 8 | 0 | 0 | 0 | 1 | 3 | 4 | Done | Target: get done by Sprint 2 - Done
Generally debug code, testing |  | All | 16 | 5 | 0 | 4 | 2 | 2 | 3 | Done | Target: get done by Sprint 2 - Done
TOTAL |  |  | 38 | 11 | 2 | 10 | 3 | 5 | 7