## Product Backlog
ITSC-3155 Software Engineering
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT # | Done?
Personalized Travel Recommendations (Andrew) | Low | 16 | Yes | Yes | 2 | TRUE
Cost-effective Trip Planning (Landon) | Medium | 12 | Yes | Yes | 2 | TRUE
User Reviews/Ratings (Ethan) | Medium | 8 | No | Yes | 1 | TRUE
Flight/Hotel Booking Integration (Dhanush + Shashank) | High | 14 | Yes | Yes | 1 | TRUE
Data preprocesing + setting up SQL database | High | 10 | No | Yes | 0 | TRUE

## User Stories
ITSC-3155 Software Engineering
User Stories
ID | FEATURE | AS A <type of user> | I WANT TO <perform some task> | SO THAT <achieve some goal> | FINAL STORY | PRIORITY | STORY POINT
1 | Personalized Travel Recommendations | End User | know about trips that align with my interests | I can plan and take trips that fit my needs and wants in what I look for in a vacation | As an end user I want to know about trips that align with my interests so that I can plan and take trips that fit my needs and wants in what I look for in a vacation. | Low | 16
2 | Cost-effective Trip Planning | End User | be aware of the price point of a number of options and be able to take action accordingly | So that we can have fairness in pricing and save money | As an end user, I want to be aware of the price point of a number of options and be able to take action accordingly, so that I can keep my trip within my budget. | Medium | 12
3 | Flight/Hotel Booking Integration | End User | be able to book what I need for a trip, all inside the app | I can conveniently and quickly prepare for my trip. | As an end user, I want to be able to book what I need for a trip, all inside the app, so I can conveniently and quicikly prepare for my trip. | High | 14
4 | User Reviews/Ratings | End User | be able to read and write user reviews about travel destinations, and ones I have travelled to | View ratings to determine if a trip is well-rated by other users | As an end user I want to be able to read and write user reviews about travel destinations, and ones I have travelled to I can determine whether I should book a trip if it is well-rated by other users. | High | 12
0
0
0
0
0
0
0
0
0
TOTAL | [6 empty] | 54